## Sheet1
Current as of: | 2021-12-08
Task # | Status | Description | Completion | Note
1 | Paused | Create a catalog of the C++ code's functionalities that need to be ported to Fortran | 95% | High-level map in doc_notes.pdf, finer details to come as necessary.
2 | Completed | Create makefile and directory organization for smooth workflow | 100% | Functionally completed, with room for improvement down the line
3 | Completed | Read in data from text files | 100% | Includes reading array size metadata and geometry-specific input files. Improvements could be made to pre-processing structure.
4 | Paused | Create variables, structures, classes, etc. | 75% | Most important variables created in simple arrays instead of complex structures. Variables will be defined as necessary.
5 | Paused | Create configuration file | 50% | File created, more items to be added as needed
6 | Completed | Enforce output directory existence | 100% | Note: Code only works on Linux
7 | In Progress | Initialize simulation
7.01 | Paused | Allocate and initialize variables | 95% | Only missing capability of starting from previous run, delayed until output format is determined
7.02 | In Progress | Enforce boundary conditions on initial conditions | 0%
7.03 | Future | Calculate flow derivatives
8 | Future | Output simulation state to files